## Summary
RSA Agent — QA Defect Summary
Severity | Count | Remediation | Count
Critical | 3 | Fixed | 14
High | 12 | Open | 32
Medium | 24 | Deferred | 4
Low | 13 | Withdrawn | 1
Total | 52 | Won't fix | 1
|  | Total | 52
Production Readiness Score | 68 / 100 (was 60)
Launch Recommendation | Needs Significant Work
Remediation status (June 23, 2026)
14 correctness/data/functional defects fixed and re-verified (342/342 offline tests pass; all Python compiles; Apps Script + webapp JS syntax-checked). 1 withdrawn (ZIP-01, false positive), 4 deferred, 1 won't-fix. 32 remain OPEN — led by the 3 Critical security items + concurrency/locking. Launch is now gated almost entirely by Security + Reliability, not correctness. Apps Script (.gs) fixes are syntax/logic-verified but need a deploy-time smoke test (no Apps Script runtime in the test env).

## Defect Log
ID | Severity | Category | Component | Location | Evidence | Title | Reproduction | Expected Behavior | Actual Behavior | Recommended Fix | Remediation
SEC-01 | Critical | Security | Config | .env.example:18 | Confirmed | Real Anthropic API key shipped in the example env template | Open .env.example (a file meant to be shared/committed); ANTHROPIC_API_KEY default is a full sk-ant-... value, not a placeholder. | Template contains only a placeholder. | A live-format secret is embedded in the shareable template. | Rotate the key immediately; replace with a placeholder; scan history; keep real secrets only in .env (already git-ignored). | Open
SEC-02 | Critical | Security | GAS endpoints / legacy JS | GAS_BotEndpoints.gs:17; rsa_agent.js:38 | Confirmed (static) | Public webhook guarded by a hardcoded default shared secret | doPost auth is `secret !== 'rsa-agent-secret-change-me'`. Same default in rsa_agent.js, and it is NOT in that file's required-env check. README deploys the web app as 'Anyone'. | Unique strong secret, verified at deploy; fail-closed when equal to the default. | If the secret was not rotated on the live deployment, anyone who reaches the URL can write the tracker and send emails. | Rotate; store in Script Property; refuse to serve when equal to the default; prefer a domain-restricted deployment. | Open
SEC-03 | Critical | Security | Webapp (Index.html) | ~1058-1071,1356-1369,1614-1621,1778-1822,863-877 | Confirmed (static) | Stored XSS: unescaped sheet/import data rendered into innerHTML | Set a Store/Notes/Cart-ID (via Add Cart form, W&M Excel import, or direct sheet edit) to `<img src=x onerror=...>`; open the Tracker/Archive/Dashboard tab. | All dynamic fields HTML-escaped; links scheme-validated. | Raw interpolation runs attacker JS in every operator's browser; reportLink href is not https-validated (techResultsLink is — inconsistent). | Add escapeHtml() + safeUrl() helpers across all renderers (or use textContent/createElement); https-allow-list every link; add rel=noopener. | Open
BUILD-01 | High | Bug | Caper extractor | caper_pdf_to_csv.py:2-3 | Confirmed (py_compile) | caper_pdf_to_csv.py does not compile; writes to a foreign path | python3 caper_pdf_to_csv.py (or import it). | Compiles; writes caper_stores.csv to the working dir. | Line 2 is a quoted-string SyntaxError; `sys` never imported; OUT hardcoded to /sessions/zealous-brave-maxwell/... (another machine). | Fix line 2 (import sys; unquote the expression); take OUT from env/CWD. The address-join key CSV currently can't be regenerated. | Fixed
DATA-01 | High | Logic | Reconcile + GAS + agent | rsa_reconcile.py:50/151/477; GAS_BotEndpoints _botAddCart:246,_botFullOnboardCart:841,844 | Confirmed (static) | Unknown state silently defaulted to NJ (and NJ forced to TRUNO) | Reconcile/onboard a store whose state can't be inferred. | Leave blank + flag for review; never guess; apply the NJ-vendor rule everywhere. | DEFAULT_STATE='NJ'; GAS state¦¦'NJ'; fullOnboard forces vendor TRUNO for NJ — contradicting the interactive 'NJ must choose vendor' rule. | Use store_map.store_state(confident); write blank+flag when not confident; enforce the NJ-vendor guard in every write path. | Fixed
DATA-02 | High | Logic | Store map | store_map.py ~321 (name pass) | Confirmed (executed) | state_from_address returns a CONFIDENTLY wrong state | Resolve 'Washington, DC' / '100 Indiana St, Chicago IL' / 'Nevada, MO' / 'Delaware, OH' (no ZIP). | ZIP -> trailing-code -> name precedence; name least-trusted. | Spelled-out state name in a city OR street beats the trailing code: ->WA, ->IN, ->NV, ->DE, all basis='name'. | Run ZIP and trailing 2-letter-code passes BEFORE the name pass; require the name near the end / after a comma. | Fixed
FUNC-01 | High | Logic/Bug | Sheets engine | rsa_sheets.py:116-136 (_find_row) | Confirmed (executed) | Loose substring cart matching edits/queries the WRONG cart | Call query_cart('1') / update_cart('1') with no store hint against real data. | Exact/anchored cart-id match; ambiguity prompts for disambiguation. | `rid==q or q in rid or rid in q` -> '1' matched P_WF_SHOPRITE_72_M3_001 (first hit). Wrong-cart writes possible. | Match exact id or anchored serial; never substring-match a bare number; require store/disambiguation on multiple hits. | Fixed
FUNC-02 | High | Logic | Drive monitors + sheets engine | drive_monitor.py _match_file; rsa_sheets._store_nums | Confirmed (executed) | Form attached to the wrong store via numeric-substring filename match | Store 'ShopRite 50'; a file named 'WF50_2050_report.pdf' in the folder. | Boundary/chain-qualified match (like the strict tech matcher). | store nums {50} intersect filename nums {50,2050} -> file matched to ShopRite 50; W&M monitor uses non-strict match and overrides the printed store. | Use match_cart_strict-style logic; require a chain token; boundary match (#50 / WF50) not substring; don't override a mismatched printed store. | Fixed
FUNC-03 | High | Logic/Bug | GAS automation | GAS_Automation.gs:770-772 | Confirmed (grep) | 'Pending' / 'Partial' inspection results recorded as 'Passed W&M' | Ingest a row whose result text is 'pending' or 'partial'. | Only explicit pass tokens count; ambiguous -> manual review. | PASS_KW includes bare 'p'; rawResult.startsWith('p') -> wmPassed=true -> writes 'Passed W&M'. | Remove bare 'p'; use an anchored explicit token list; ambiguous results never auto-pass. | Fixed
FUNC-04 | High | Logic | GAS automation | GAS_Automation.gs:545-551 | Confirmed (grep) | CSM nudge re-pings carts that already FAILED W&M | A cart with rsaStatus 'Completed RSA' and wmStatus 'Failed W&M'; run checkCompletedVisits. | Exclude any attempted/terminal W&M status. | Exclusion set is only {Passed W&M, Completed W&M}; 'Failed W&M' keeps matching -> endless 'schedule W&M' alerts to the CSM alias. | Alert only when wmStatus is empty/'Pending W&M'; exclude Failed/Passed/Completed. | Fixed
REL-01 | High | Reliability | Sheets engine + GAS + monitors | _next_row/update_cart; _botAddCart/_botScheduleTruno; monitorTrunoTracker; processed_*.json | Confirmed (static) | No locking: concurrent writers clobber rows / duplicate side-effects | Two onboard messages in parallel (Slack Bolt is multi-threaded), or a GAS trigger + Python monitor writing the same row. | Serialized writes (LockService / lock); atomic processed files; column ownership. | Read-then-write next-row scans and cross-process writers with no LockService/atomic writes; processed_*.json truncates in place. | LockService.tryLock in GAS; lock + os.replace for processed files; designate per-column ownership across GAS/Python. | Open
REL-02 | High | Reliability | GAS automation | GAS_Automation.gs:70-82,1121-1130 | Confirmed (static) | Overlapping automation triggers double-run monitors | monitorTrunoTracker/ingestInspectionFiles fire via their own triggers AND masterDailyRun near 9am. | Single ownership + lock so a concurrent run is skipped. | No LockService; Script-Property idempotency read at start of each run -> overlapping runs can double-email/Slack/write. | Drive each monitor from one path only; wrap bodies in LockService.tryLock(0). | Open
REL-03 | High | Reliability/Bug | GAS automation | GAS_Automation.gs:655-708 | Static (high-confidence) | Excel ingest broken for true .xlsx; file marked processed on zero rows | Drop a real binary .xlsx W&M form in the inspection folder; run ingestInspectionFiles. | Convert xlsx->Google Sheet then export; mark processed only when rows were imported. | export?format=csv only works for native Sheets; binary fallback yields garbage; ingested[fileId] set even on zero rows -> never retried; errors only logged. | Drive.Files.copy to a Sheet then export; gate marking on rows>0; Slack-alert on zero-row ingest. | Open
SEC-04 | High | Security | Agent (Slack) | rsa_agent.py:956-971 | Confirmed (static) | No authorization allowlist on the bot | Any workspace member DMs or @mentions the bot with an onboard/update command. | Allowlist of authorized users/channels checked before acting. | user_id is captured only for the display name; any member (incl. guests in shared channels) can write prod and trigger emails to Nicole. | Env-configured user/channel allowlist enforced before handle_message. | Open
VIS-01 | High | Logic | GAS tracker view | Code_getTrackerData.gs:65-73 | Confirmed (grep) | Dashboard hides active-but-aging W&M carts after 30 days | A cart 'Completed RSA' + 'Pending W&M' whose RSA completed >30 days ago. | Hide only when overallStatus === 'Passed' (truly done). | isPassed = Passed OR rsaStatus=='Completed RSA' OR wmStatus=='Passed W&M'; such carts are dropped though W&M is still open. | Treat as hideable only on true completion; keep anything with an open W&M visible. | Fixed
ADDR-01 | Medium | Logic | Store map | store_map.py:61-76 (addr_key) | Static | addr_key collides distinct tenants sharing street#+ZIP | Two stores at the same plaza address/ZIP. | Incorporate suite/unit, or fall through to full-string compare. | house¦zip key collapses different stores -> wrong Caper<->Truno join (the failure the join was meant to prevent). | Suite-aware key; full-string fallback when a house¦zip cluster has >1 row. | Deferred
ARCH-01 | Medium | Performance/Reliability | GAS automation | GAS_Automation.gs:872 | Static | Ingest creates an unbounded new tab per file | Let ingestInspectionFiles run 4-hourly for months. | Rotate/cap archive tabs or use a rolling log. | insertSheet per file with no pruning -> eventual cell/tab cap and insertSheet failures. | Keep last N tabs or append to one Ingest Log sheet. | Open
AUDIT-01 | Medium | Logic | Store map / verify | store_map.build:225; verify_addr.py | Static | verify_addr disagrees with reconcile (number fallback) | Run verify_addr vs trace_truno for the same store. | Pre-flight matches what reconcile will actually do. | verify uses the number fallback reconcile abandoned, overstating clean matches. | Drive verify off a reconcile dry-run. | Open
COL-01 | Medium | Logic/UX | Sheets engine | rsa_sheets.py:452,75 | Static | W&M report link written into the 'Tech Upload Link' column | Apply a W&M test result with a report link. | Distinct, clearly named link columns. | set_test_result writes the report link to C_TECH_LINK (col T, labeled 'Tech Upload Link'), conflating it with the tech link in col W. | Clarify the column purpose/name; separate W&M and tech links. | Open
COL-02 | Medium | Bug | Sheets engine | rsa_sheets.py:543,563,505 | Static | Gap counters read a default column if header not yet resolved | Call carts_missing_results()/results_completeness() before ensure_tech_results_columns(). | Resolve the Tech Results header before counting. | _tech_cols() falls back to V/W; if Tech Results was appended at another column, counts read the wrong column. | Resolve/ensure the header before reading the gap counts. | Fixed
DAYS-01 | Medium | Bug | GAS automation | GAS_Automation.gs:560,564-565 | Confirmed (grep) | CSM alert shows column-P raw value as the 'days' count | Trigger a CSM nudge and read the '(Nd)' figure. | Show the computed days-pending. | Pushes r[15] (col P) instead of the computed daysSince -> '(Nd)'/'NaNd in status'. | Carry the computed daysSince into the alert payload. | Fixed
DEL-01 | Medium | Reliability/Security | Webapp + GAS automation | Index.html deleteCartRecord; GAS_Automation.gs:1007 | Static | Hard delete with weak audit and no soft-delete | Click Delete in the edit modal. | Soft-delete (Archive) + authz + real audit. | deleteRow keyed by exact cartId; only a Logger line; anonymous if the web app is 'Anyone'. | Move deletes to an Archive sheet; add authz + an audit record. | Open
DUP-01 | Medium | Reliability | GAS endpoints + automation | _botScheduleTruno:654; emailNicoleForNewTrunoRows | Static | Two email-to-Nicole paths can double-send | Anything that calls doPost scheduletruno/fullonboard while the 15-min email trigger is also enabled. | One canonical email path with a sent-flag guard. | Python path relies on the trigger to email; the GAS endpoint also emails directly -> potential duplicate vendor emails. | Pick one path; guard with a 'Nicole emailed' flag column. | Open
ENC-01 | Medium | Reliability/Bug | GAS automation | GAS_Automation.gs:676,760-781,862 | Static | CSV ingest UTF-8 only; ambiguous locale date parsing | Ingest a Windows-1252 CSV, or a dd/MM date. | Charset detection; parse to real Date objects. | Latin-1 mojibake; MM/dd vs dd/MM ambiguity; string dates break checkCompletedVisits (expects Date) so those rows never alert. | Detect charset; use Utilities.parseDate; store real Dates. | Deferred
IDEMP-01 | Medium | Logic/Idempotency | Reconcile | rsa_reconcile.py:316-326,413,461 | Static | Reconcile can create duplicate carts for one store+cart | Two Truno rows for one store that resolve to slightly different store names across runs. | Derive the serial from a stable store#+chain and existence-test it. | Existence check uses many identifiers, but the net-new serial is derived from a single chosen display name -> mismatched serials evade the dedup. | Key the serial off store number+chain; test the derived serial before adding. | Deferred
IDEMP-02 | Medium | Logic | GAS automation | GAS_Automation.gs:133-135 | Static | Truno reschedule replays the same key -> ETS reminder skipped | Schedule -> cancel -> re-schedule a visit to a new date. | Key includes date/version; cancel clears the scheduled key. | rowSig = store¦cart¦status has no date; the re-schedule reuses the key and is skipped, so the ETS Coffee-Break reminder for the real date never posts. | Version the idempotency key with the visit date. | Fixed
MARK-01 | Medium | Logic | Drive monitor | drive_monitor.py:184-187 | Static | 'Missing form' warning fires once ever and never re-warns | A forms-sent store with no matching file across many days. | Re-warn after N days. | A 'missing:'+slug marker is stored in the processed set forever; a still-missing form is never re-flagged. | Track missing-store warnings with a timestamp and re-warn after a threshold. | Fixed
PERF-01 | Medium | Performance | GAS automation | GAS_Automation.gs:106,204-205 | Static | monitorTrunoTracker does O(Truno x Tracker) full-allocation scans | Run with a large Truno sheet and default 1000-row allocation. | getLastRow bound; read the tracker once per run. | Uses getMaxRows() and re-reads the tracker per Truno row -> thousands of getValues, near the 6-min limit. | Use getLastRow(); hoist the tracker read out of the per-row matcher. | Open
PERF-02 | Medium | Performance | Store map / reconcile | store_map.resolve:115 | Static | Overrides JSON parsed on every row during reconcile | Reconcile a large Truno sheet. | Load overrides once. | _overrides()/_state_overrides() open+parse store_map.json per cart -> many file reads; widens the unlocked-write race. | Memoize overrides (mtime-checked) or pass them in. | Open
REL-04 | Medium | Reliability | Drive/Tech monitors | drive_monitor.py:63-76; tech_monitor.py:60-73 | Static | processed_*.json read-modify-write is non-atomic and unlocked | Run a --backfill while the background poller is running, or crash mid-write. | Atomic temp+os.replace; single-writer lock. | open(...,'w') truncates in place; crash -> empty set -> reprocess everything; concurrent runs clobber. | Atomic write + lock; or have the CLI talk to the running poller. | Open
REL-05 | Medium | Reliability | Sheets/Drive/JS network | gspread calls; drive get_media; rsa_agent.js fetch | Static | No timeouts/retries/backoff on Sheets/Drive/GAS calls | Transient 5xx/timeout during a write or backfill. | Retries with backoff + timeouts; partial-write handling. | A blip aborts a run or hangs (stuck Slack hourglass); batched writes can leave the sheet half-updated. | Add num_retries/timeout/backoff; document or eliminate partial-write windows. | Open
ROUTE-01 | Medium | Logic | Agent | rsa_agent.py:868-880 | Confirmed (executed) | W&M form saved as .xlsx is misrouted to the tech/calibration path | Upload 'Shoprite_scale_test.xlsx' with caption 'results attached' (no keyword). | Route by content, or warn on ambiguity. | Extension rule sends any spreadsheet to tech; W&M pass/fail processed as calibration. (An explicit 'w&m' caption correctly overrides.) | Detect by content/headers; warn on ambiguous; document the precedence. | Fixed
SEC-05 | Medium | Security | Webapp + GAS automation | Index.html:1421-1432; GAS_Automation.gs:788-790 | Static | CSV/formula injection on export and GAS HYPERLINK | Set Notes to '=HYPERLINK("http://evil","x")' or '=IMPORTRANGE(...)'; export CSV / let ingest build the link. | Neutralize leading = + - @; escape quotes or use RichText links. | Export only quotes commas/quotes; filenames are interpolated into setFormula unescaped. | Prefix-guard CSV fields; escape quotes / use newRichTextValue().setLinkUrl(). | Open
SEC-06 | Medium | Security | GAS endpoints | _buildTrunoEmail/_buildWinterScalesEmail (~1010,1119) | Static | HTML injection into outbound vendor emails | Include HTML/script in a cart note or store name on an onboard. | Escape user-controlled fields before embedding in htmlBody. | store/notes/address/submittedBy interpolated raw into the email HTML body. | HTML-escape all interpolated values. | Open
STATE-DUP | Medium | Logic | Reconcile vs store map | rsa_reconcile._state_from_addr vs store_map.state_from_address | Static | Two divergent state-from-address parsers | Same address through reconcile vs the agent. | One shared, conservative parser. | Reconcile uses its own looser last-2-letter-token scan; the two implementations disagree. | Call store_map.state_from_address from reconcile; delete the duplicate. | Deferred
UNDO-01 | Medium | Reliability | Undo tool | rsa_undo.py:55,61-68 | Static | Undo deletes on a fragile Notes prefix with no backup | Run rsa_undo --commit after a human edited a backfilled row's Notes. | Match a machine-only marker; snapshot before delete. | Sole criterion is Notes.startswith(tag); over/under-deletes; no backup beyond stdout. | Use a dedicated marker column; export matched rows to CSV before deleting. | Open
UX-01 | Medium | UX/Reliability | Agent | rsa_agent.py:771-802 | Static | No confirmation before a write+schedule+email onboard | Send 'launch cart 5 at WF 9 PA, trigger Launches' (non-NJ, trigger stated). | A confirm step before irreversible side effects. | Onboards immediately: writes tracker + Truno row + (15-min trigger) emails Nicole. One LLM misclassification triggers all of it. | Add a Block Kit confirm button for onboardCart before writing/emailing. | Open
UX-02 | Medium | UX/Feature gap | Webapp | Index.html:563,571 vs 2019 | Confirmed (static) | Add Cart form silently drops 'Overall Status' and 'DRI' | Set Overall Status + DRI on the Add Cart form; submit. | Values persist or the fields are removed. | The addCartManual payload omits overallStatus and dri; the values are discarded. | Include both in the payload, or remove the fields. | Fixed
ZIP-01 | Medium | Logic/Data | Store map | store_map.py _ZIP3_RANGES | Confirmed (executed) | state_from_zip missing several assigned ZIP prefixes | Resolve 42801(KY), 26901(WV), 57801(SD), 58901(ND), 69401(NE), 84801/84901(AZ). | Full prefix coverage. | All return None (fail-safe), forcing an unnecessary 'what state?' prompt for valid ZIPs. | Extend the ranges or use a ZIP dataset library. | Withdrawn
A11Y-01 | Low | Accessibility | Webapp | Index.html nav/modal/rows | Static | Keyboard/screen-reader gaps | Navigate the app with keyboard only / a screen reader. | WCAG-compliant controls. | divs/spans with onclick (no role/tabindex/keydown); modal lacks focus trap, Esc, aria-modal; icon-only buttons unlabeled. | Use buttons/anchors; add roles/tabindex/keydown; modal focus trap + Esc + aria; aria-labels. | Open
DATE-JS-01 | Low | Bug | GAS tracker view | Code_getTrackerData.gs:49-54 | Static | Locale-ambiguous date parsing in asDate | A cart date in an ambiguous MM/dd vs dd/MM form. | Explicit Utilities.parseDate format. | new Date(v) on arbitrary strings; the 30-day completion window can be off by months. | Parse with an explicit format given the known sheet format. | Open
DOC-01 | Low | Documentation | Tests / config | tests/README.md; .env.example:21 vs rsa_agent.py:48 | Confirmed | Docs drift: stale test counts and model default mismatch | Compare documented vs actual. | Docs match reality. | Docs say 81/63 passing; actual is 179/91. .env.example default model is sonnet-4-6; code default is opus-4-8. | Update the counts and reconcile the model default. | Open
ETS-01 | Low | UX | GAS automation | GAS_Automation.gs:31,61,399 | Static | ETS reminders post to the W&M channel/usergroup (placeholders) | Trigger an ETS Coffee-Break reminder. | Dedicated ETS channel + usergroup. | ETS_SLACK_CHANNEL_ID aliases the W&M channel and tags the W&M usergroup. | Configure real ETS channel/usergroup before launch. | Open
GW-01 | Low | Security | Agent / tech forms | rsa_agent.py:47; tech_forms.py:39 | Static | Credential-like default + hardcoded internal gateway URL | Run without AIGATEWAY_API_KEY. | Empty default; fail loudly if auth ever required. | Default 'gateway-no-token-needed'; internal aigateway.instacart.tools URL hardcoded (auth is by network today). | Default empty; keep internal URLs in env. | Open
LEGACY-01 | Low | Reliability/Security | Legacy JS bot | rsa_agent.js (whole) | Static | Dead/legacy Slack bot retained alongside the active Python agent | Inspect rsa_agent.js vs rsa_agent.py. | Remove or clearly quarantine superseded code. | rsa_agent.js is the old GAS-webhook architecture (hardcoded secret default, parseIntent throws on non-JSON, frozen system-prompt date); superseded by rsa_agent.py. | Delete it or move to /legacy with a README note; ensure it can't be run by mistake. | Open
NOOPENER-01 | Low | Security | Webapp | Index.html target=_blank anchors | Static | target=_blank links lack rel=noopener | Open any external link from the app. | rel=noopener noreferrer on all _blank links. | Reverse tabnabbing; compounded by the unvalidated reportLink href. | Add rel=noopener noreferrer everywhere. | Open
NULLGUARD-01 | Low | Reliability | Webapp | Index.html 1393-1396,1978-1980,1870-1873,1590-1597 | Static | Success handlers lack null guards (NPE on null/blank data) | Server returns null, or a dashboard row has a blank status. | if(!res¦¦res.error) guards; (r.x¦¦'') everywhere. | Archive/AddCart/processWM handlers and buildStats deref without guards -> uncaught errors, button left stuck, dashboard breaks on one blank cell. | Add uniform null guards; use (r.field¦¦''). | Open
RESP-01 | Low | UX | Webapp | Index.html styles (no @media) | Static | No responsive layout despite a mobile viewport tag | Open the app on a phone/narrow window. | Responsive breakpoints. | Fixed 220px sidebar + hard 5/3/2-column grids overflow on small screens. | Add @media breakpoints; collapse sidebar; auto-fit grids. | Open
ROB-01 | Low | Reliability | Store map | store_map.py:106-107,334-341 | Static | Bare excepts silently treat a corrupt overrides file as empty | Corrupt store_map.json, then resolve a store. | Distinguish missing vs corrupt; warn on JSONDecodeError. | except Exception: return {} -> all manual mappings silently discarded. | Catch FileNotFoundError separately; log on parse errors. | Open
UX-03 | Low | UX | Webapp | Index.html alert()/confirm() | Static | Inconsistent feedback model (native dialogs vs inline alerts) | Run archive / delete / empty-CSV flows. | One consistent inline-alert pattern. | Mix of blocking native dialogs and inline alerts; native dialogs can overflow. | Standardize on the inline alert components already present. | Open
VENDOR-01 | Low | Logic | Sheets engine | rsa_sheets.py:580-594 (_norm_vendor) | Confirmed (executed) | Unknown vendor text stored verbatim | Pass rsaVendor='Acme Scales Inc'. | Map to a known vendor or TBD; flag unknown. | _norm_vendor returns unrecognized input unchanged -> arbitrary text in the vendor column. | Whitelist vendors; unknown -> TBD + flag. | Won't fix
VIS-02 | Low | Reliability | Tech/test forms | tech_forms.py:261-265 | Static | Fragile vision-JSON de-fencing with no retry | Model returns prose around the JSON or a trailing comma. | Brace-scan extraction / structured output / one retry. | json.loads after 3 regexes; failure drops the whole form (self-heal then retries forever). | Extract the first balanced object; request JSON mode; retry once. | Open

## Verification Notes
Claim | Verdict | Evidence
CSM 'passed' key absent (subagent claim) | REFUTED | test_forms.py emits 'passed' (lines 142/146) and drive_monitor._fmt consumes it (217); the Passed->Pending W&M (cc CSM) line works on both paths.
rsa_agent.py JSON parse crash (by analogy to rsa_agent.js) | REFUTED | _extract_json has a balanced-brace fallback and parse_intent never raises; verified across 8 adversarial inputs.
ZIP gaps at 420/268/574/588/688/850 (adjacent prefixes) | CORRECTED | Those resolve correctly; the real gaps are 428/269/578/589/694/848/849 (see ZIP-01).